## Sheet1
Task Name | Phase | Start Date | End Date | Assignee | Depends On | Location
Define project scope | Planning | 2025-01-07 | 2025-01-15 | Alice |  | New York
Create wireframes | Design | 2025-04-17 | 2025-04-19 | Bob | Define project scope | Phoenix
Design UI mockups | Design | 2025-02-20 | 2025-02-23 | Bob | Create wireframes | Beijing
Set up project repo | Development | 2025-04-17 | 2025-04-18 | Alice | Define project scope | Shanghai
Frontend development | Development | 2025-07-24 | 2025-07-30 | Charlie | Design UI mockups, Set up project repo | Chicago
Backend development | Development | 2025-04-24 | 2025-04-30 | Dana | Set up project repo | Boston
Integrate frontend/backend | Development | 2025-05-01 | 2025-05-03 | Charlie, Dana | Frontend development, Backend development | Los Angeles
Write unit tests | Testing | 2025-09-04 | 2025-09-05 | Erin | Integrate frontend/backend | remote
User acceptance testing | Testing | 2025-08-06 | 2025-08-08 | Bob | Write unit tests | remote
Final fixes & deploy MVP | Launch | 2025-11-08 | 2025-11-10 | Alice | User acceptance testing | remote